## Slide 1
AMG MANUFACTURING
ERP Transformation
Decision deck: scope, outcomes, risk, readiness
Board Steering Committee · April 2026

## Slide 2
AMG · ERP TRANSFORMATION
Agenda
02 / 12
Confidential · Transformation Office · Board Pre-Read
What this deck covers
01
The problem we are solving
Why now, what breaks if we wait
02
Guiding principles
Standard before custom, value before vanity
03
Plan & two-wave roadmap
12-month core go-live + 2-month Wave 2 optimization
04
Measurable outcomes
Eight KPI commitments
05
Day-1 scope vs deferred
What we are NOT doing, and why
06
Risks & cutover gates
Five gates, one rollback
07
Decision requested
Approvals, governance, contingency

## Slide 3
AMG · ERP TRANSFORMATION
Context
03 / 12
Confidential · Transformation Office · Board Pre-Read
The cost of standing still
Symptoms across finance, supply chain, and the plants
11 days
to close the books
monthly, with 1,420 manual JEs
4.8%
BOM error rate
released to production
67 days
of inventory
tied up in working capital
23
legacy systems
integrated by 140 point-to-point links
Bottom line: the legacy stack is the bottleneck on growth, M&A integration, and audit readiness.
Cost of inaction (planning assumption, to be re-baselined at detailed design): $14-18M per year in working capital drag, rework, and audit remediation.

## Slide 4
AMG · ERP TRANSFORMATION
Guiding principles
04 / 12
Confidential · Transformation Office · Board Pre-Read
Four principles that govern every decision
01
Standard before custom
Adopt vendor best-practice processes; customize only where audited differentiation exists.
02
One source of truth
Single global COA, item master, customer master. No regional forks.
03
Readiness over date
Cutover moves if any of five gates is not green. The date is an output, not an input.
04
Value before vanity
Every scope item maps to one of eight KPIs, or it does not enter Day-1.

## Slide 5
AMG · ERP TRANSFORMATION
Roadmap
05 / 12
Confidential · Transformation Office · Board Pre-Read
12-month core go-live + 2-month Wave 2 optimization
Wave 1 stabilizes the core. Wave 2 extends the value.
Mobilize
M1-M3
Design
Build
M4-M7
Configure & integrate
Test
M8-M9
SIT, UAT, mock cutovers
Go-Live
M10
Wave 1: Finance, P2P, Plants
Care
M11-M12
Hypercare 1:25 ratio
Wave 2
M13-M14
APS · Quality · Supplier portal (optimization)
Cutover gate review (Steering Committee) at M9.
12-month figure refers to core go-live (M10) under Wave 1; Wave 2 optimization completes by M14. Date moves only if a readiness gate is not green at M9.

## Slide 6
AMG · ERP TRANSFORMATION
Outcomes - measurable
06 / 12
Confidential · Transformation Office · Board Pre-Read
Eight KPI commitments, 12 months post Go-Live
Contractual in the SI statement of work · tracked monthly
Metric | Baseline | Target | Δ
Financial close cycle | 11 days | 5 days | -55%
BOM error rate (released) | 4.8% | ≤1.0% | -79%
On-time-in-full (OTIF) | 82% | 94% | +12 pts
Inventory days of supply | 67 days | 48 days | -28%
Order-to-cash cycle | 38 days | 26 days | -32%
Manual journal entries / mo | 1,420 | ≤350 | -75%
Procurement PO touch time | 9.2 min | 3.0 min | -67%
Legacy app footprint | 23 sys | 9 sys | -61%
Value Realization Office reports KPI deltas to Steering monthly; ≥6 of 8 green required by M+12. Baselines are AMG-validated; target deltas are planning commitments.

## Slide 7
AMG · ERP TRANSFORMATION
Day-1 scope
07 / 12
Confidential · Transformation Office · Board Pre-Read
What goes live in Wave 1
Stabilize the core; protect the close; clean the data
Finance
GL · AP · AR · FA
Single global COA
Statutory in 7 countries (planning assumption)
Daily close readiness
Procure-to-Pay
Catalog & contracts
3-way match
Top-40 suppliers EDI
Approval workflows
Plant Operations
Item master & BOM
Production orders
Inventory & WMS-lite
MES via middleware
Order-to-Cash
Customer master
Pricing & rebates
Shipping & invoicing
Credit management

## Slide 8
AMG · ERP TRANSFORMATION
Scope discipline
08 / 12
Confidential · Transformation Office · Board Pre-Read
What we are NOT doing on Day-1
Five deferrals, each protects the cutover and the eight KPIs
Deferred item | Why deferred (risk/cost logic) | Re-entry
Advanced Planning & Scheduling (APS) | Needs 6 mo. of clean demand history from new ERP | Wave 2, M+6
Supplier portal & EDI long-tail | Top-40 suppliers cover ~86% of spend; 200+ endpoints not worth cutover risk | Wave 2, M+8
Shop-floor MES re-platform | Current MES stable; doubling plant change-impact would jeopardize OTIF | FY27 separate program
Global HR / Payroll consolidation | Out of value thesis; payroll risk in in-scope jurisdictions is unacceptable at cutover | Not in program
AI/ML demand sensing | Premature without stabilized data; distracts from adoption | Wave 2, M+9
Net effect: ~$4.1M Day-1 cost removed · ~38% cutover-weekend integrations · clean foundation for Wave 2
Cost and integration figures are program planning estimates, refined at detailed design.

## Slide 9
AMG · ERP TRANSFORMATION
Data continuity
09 / 12
Confidential · Transformation Office · Board Pre-Read
From 23 legacy systems to one source of truth (planning assumption)
Cleanse · convert · reconcile · sign-off
1. Profile
Assess 23 sources; rank by KPI impact
›
2. Cleanse
Owner-led sprints on item, customer, vendor
›
3. Convert
Repeatable mock loads (4 cycles)
›
4. Reconcile
Dual-run finance close for 2 periods
›
5. Sign-off
Controller, Site GM, CIO formally accept
Gate: ≥99.5% master-data accuracy on item, customer, vendor, GL, independently audited.

## Slide 10
AMG · ERP TRANSFORMATION
Risk & readiness
10 / 12
Confidential · Transformation Office · Board Pre-Read
Five cutover gates · top three residual risks
Five gates (all must be green 30 days prior)
1
Data
≥99.5% master-data accuracy; full reconciliation
2
Process
Two mock cutovers; zero Sev-1 defects
3
People
≥95% role-based training; key-user certification
4
Technology
1.5× peak load; DR proven; pen-test closed
5
Business
Order book / inventory / aging frozen; rollback signed
Top three residual risks
Data quality at conversion
Mitigation: Cleansing sprints + dual-run finance close for 2 periods
Plant change adoption
Mitigation: Site key-user network; hypercare staffed at 1:25 ratio
MES integration latency
Mitigation: Middleware queue + 30-day fallback to legacy posting

## Slide 11
AMG · ERP TRANSFORMATION
Governance
11 / 12
Confidential · Transformation Office · Board Pre-Read
Decisions go where the accountability lives
Steering Committee
Monthly
CEO chair · CFO · CIO · COO · 2 site GMs
Program Board
Bi-weekly
CIO chair · Domain leads · SI partner
Workstream Leads
Weekly
Finance · P2P · Plant Ops · OTC · Data
Value Realization Office
Monthly
Owns 8 KPIs end-to-end
Contingency reserve: 12% of program cost, held centrally, released only by Steering.

## Slide 12
AMG · ERP TRANSFORMATION
Decision
12 / 12
Confidential · Transformation Office · Board Pre-Read
Decision requested today
A
Approve program funding and governance as scoped.
B
Endorse the eight KPI commitments as contractual targets.
C
Approve the deferred-scope list, five items out of Day-1.
D
Authorize Steering to move the cutover date if any of the five gates is not green at M9.
Recommendation: APPROVE all four.